## Sheet1
S. No.	Date	Details of Observation	Status	Remarks	Menu Name	Comments by Tester
1	10-Jun-22	Once a new lead is added, some button should be there to go to it's edit action else once has to do repeated work to click on lead then find the desired customer and then click on edit. This is a lengthy process to add more details about the customer.	Open	Done
2	10-Jun-22	Space is not getting removed from mobile number, system should not allow space or special characters.	Open	Done
3	10-Jun-22	1.5 Cr to 2 Cr missing from Budget	Open	Done
4	10-Jun-22	Relationship is by default getting selected and same is happening with Emergency Contact Name.	Open	Pending
5	10-Jun-22	Option to provide multiple name and number should be available for each customer.	Open	Pending
6	10-Jun-22	Booking date and Booking amount should be at last of Update leads	Open	Done
7	10-Jun-22	From the Update Lead page user should have option to go back to the histor of same customer or go back to leads page.	Open	Done
8	10-Jun-22	The first Customer Interaction is not getting captured any where while it was entered during Leads Creation and same is happening with Customer Profile.	Open	Done
9	10-Jun-22	How will Bulk Upload Status Appear in Dashboard	Open	Pending
10	10-Jun-22	What is Preference Type in Update Lead	Open	Done
11	10-Jun-22	In Dashboard - Leads - Time is not getting captured	Open	Done
12	10-Jun-22	Emergecy Contact Name | Relationship | Number	Open	Done	Add | update Employee
13	10-Jun-22	Redirect button required on history update page.	Open	Done
14	10-Jun-22	Last Contacted Time | Creation time and Follow up time	Open	Done
15	10-Jun-22	Next Follow up - Yellow and Red(When follow time over)	Open	Done
16	10-Jun-22	Mobile Number should be clickable and open in dialer	Open	Done
17	10-Jun-22	Lead Type - Lead Table	Open	Done
18	10-Jun-22	Lead -> Assigned Lead	Open	Done
19	10-Jun-22	Lead Add - Checkbox -> Featured	Open	Done
20	10-Jun-22	Show Green Star on name for Featured leads- Admin	Open	Done
21	10-Jun-22	Lead -Action | Edit and History - Before Data	Open	Done
22	10-Jun-22	Lead History - Edit Lead button and Update History button	Open	Done
23	10-Jun-22	Remove Customer Profile from history and Add it in information section,Show all lead information like 9 and show more button to show all information.	Open	Done
24	10-Jun-22	Contact Number | Alt Contact Number 1 and Alt Contact Number 2	Open	Done
25	10-Jun-22	Location of Customer	Open	Done
26	10-Jun-22	Project Type - Customer Requirement	Open	Done
27	10-Jun-22	Project Dropdown with multiple Selection - Update History page	Open	Done
28	10-Jun-22	FLAT 1 BHK RTM - FLAT 4 BHK RTM	Open	Done
29	10-Jun-22	FLAT 1 BHK UC - FLAT 4 BHK UC	Open	Done
30	10-Jun-22	Reference - Reference Name | Reference Contact Number	Open	Done
31	10-Jun-22	Customer Type - TENANT AND OWNER	Open	Done
32	10-Jun-22	Customer if Seleted TENANT OR OWNER - Then show Rent Budget Field	Open	Done
33	10-Jun-22	Regular Investor - YES | NO - Lead Section	Open	Done
34	10-Jun-22	Emergency Contact Name - USING MOBILE NUMBER RELATIONSHIP Added	Open	Pending
35	10-Jun-22	Booked In Project - Dropdown	Open	Done
36	10-Jun-22	History Count and	Open	Done
37	10-Jun-22	Multiple Project Booking Option	Open	Done
38	10-Jun-22	User ID/Name should also appear in History Information for each entry.	Open			Not Done
39	10-Jun-22	Action Button should be available in Dashboard Leads section too	Open			Done
40	10-Jun-22	Leads Information & Status History - Can be aligned towards left side so that more collumns can appear as of now too much space is wasted in extreme left. Should be aligned properly	Design Part			To check with Tofik
41	10-Jun-22	If a number is searched and no data is fount then there shuld be a button to Add New - as soon as add new is clicked after the number searched which is not in records, it should pick the search number in contact no to create a new lead so that same number need not be written again. This will save time of user	Open			Not Done
42	29-Jun-22	Create Project - Registration Email, Registration Contact No. to be made non mandatory.	04-Jul-22			Registration Email is mandatory with asterik, Showing validation.
43	29-Jun-22	Create Project - Category - Luxury, Standard, Affordable	04-Jul-22			Done
44	29-Jun-22	Create Project - Team - Date of birth, Wedding Anniversary to be made non madatory	04-Jul-22			Done
45	29-Jun-22	Create Project - Team - Team Name should be Renamed as Sales Person Name	04-Jul-22			Done
46	29-Jun-22	Create Project - Team: Team should be renamed to Builder Team Details	04-Jul-22			Done
47	29-Jun-22	Create Project & Team should be independent. As of now on filling the project details one has to fill the Team details as well.	Open			Done
48	29-Jun-22	Create Project - All date formats should be DD-MMM-YYYY eg. 01-JAN-2022 currently date format is all together different	Open
49	29-Jun-22	All date formats should be DD-MMM-YYYY eg. 01-JAN-2022 currently date format is all together different	Open
50	29-Jun-22	Create Project - Once project is created and if we want to edit the project information, on the edit page Alternate Contact Number must be non mandatory in both places in Edit Project page . Currently it is mandatory	04-Jul-22			Done
51	29-Jun-22	On editing the Project Information it is not showing the already selected fields instead asked to reselect Catagory, Project Type once again.	04-Jul-22			Done
52	29-Jun-22	Create Project - If Project Name is Different but Registration Email & Registration Contact Number are same then it gives error The email has already been taken & The contact number has already been taken.	Open			Done
53	29-Jun-22	Create Project - Under Create Project - Team ( Builder Team Details ) should be indipendent. While adding the Team (Builder Team Details) there should be option to select the Projects for that particular Team Member	Open			Right now in progress.
54	29-Jun-22	Employees - Create Employee - While Creating Employee only Administrator Role is appearing	Open			Done
55	29-Jun-22	Employees - Create Employee - Marriage Anniversary should be non mandatory	04-Jul-22			Done
56	29-Jun-22	Employees - Create Employee - Form & Edit Employee Forms are different. Both should be in same sequence	04-Jul-22			Done, Password/Confirm Password are only in Create Form
57	29-Jun-22	Employees - Edit Employee : Emergency Contact Number field gets automatically gets filled with oninput="this.value	04-Jul-22			Done
58	29-Jun-22	Employees - Edit Employee: Relationship field gets automatically gets filled with Father	04-Jul-22			Done
59	29-Jun-22	Leads Create - Source: YouTube, Walk-in Project Site, Walk-in Office, Referral, Channel Partners, Sub Broker, Cold Calling, Developer Leads, Facebook, Instagram, Twitter, Canopy, Catchers, Outdoor Display, Events, Corporate, Affiliate Marketing, News Papers Ads, Auto Dailers Campaign, SMS Campaign, WhatsApp Campaign, Digital Ad Leads YouTube, Digital Ad Leads Facebook, Digital Ad Leads Instagram, Digital Ad Leads Twitter, Web Portal, Others	Open			unable to scroll and see all source fields, To Apply Scroll View in DropDown.
60	29-Jun-22	Leads Create - Lead Status:	Open			Prakhar has to do it
61	29-Jun-2022	Show more button in Lead Creation form needed	Open			Done
62	29-Jun-2022	Leads Create: Lead Status: New, Pending, Call Not Answered, Next Follow-up, Site Visit Conducted, Unable to Connect, Case Closed - Enquiry Only, Case Closed - Not Interested, Case Closed - Low Budget, Case Closed - For Common Pool, Reallocate from Common Pool, Booking Confirmed, Booking Cancelled,	Open			Done
63	29-Jun-2022	Lead Create: Lead Status - Any Lead Status for any lead entered 1st time in system should show as NEW	Open			Not Done
64	29-Jun-2022	How we will view all resale which should be visible to all.	Open
65	29-Jun-2022	Leads Create Page & Update Leads pages should have same sequence - Check Sheet 2 for Sequence	Open
66	29-Jun-2022	In Leads - Leads Create & Update Leads - Relationship Dropdown should have below sequence: Self, Father, Mother, Brother, Sister, Cousin Brother, Cousing Sister, Son, Daughter, Uncle, Aunty, Grandparents, Others	Open			Done
67	29-Jun-2022	Once Booking is done we need to route this lead to billing & accounts - how it will be done. we will give the fields	Open			Not Done
68	29-Jun-2022	Final Sequence of Leads Create, Update Leads, Leads Information -Regular Investor: In Dropdown - Yes, No (By Default No should be Selected)	Open			Done
69	29-Jun-2022	When individual cases are viewed - Button should be there to move to Previous Case or Next Case or by simply left or right scroll	Open			Done
70	29-Jun-2022	Email id of team with domain @homents.in needs to be created	Open			Not Done
71	04-Jul-22	Builder Team Details(Optional) - Add Designation List : Upper Mgmt., Middle Mgmt., Sales Team, Team Lead, CRM Team, Billing Team, Marketing Team;	Open			Done
72	04-Jul-22	Create| Update | View | Delete | History.Update | History View | - Access Role	Open			Done
73	04-Jul-22	Location should be last option in Employee ADD and Edit	Open			Done
74	07-Jul-22	From Create Project - Remove Builder Team Details Option completely as Builder Team tab has been created alreadt. Add just one firled after RERA Number i.e. Name of Developer	Open			Not Done
75	07-Jul-22	Project - Pagination to be enabled in	Open			Done
76	07-Jul-22	Edit Project not working properly. While editing Project M3M some other project is getting in edit mode	Open			Done
77	07-Jul-22	Create Project: Builder Name dorpdown to be provided in Create Project	Open			Not Done
78	07-Jul-22	Create Project: Category field is mandatory however where creating a roject we are able to leave this field empty. On leaving this field empty system should give error to select Category	Open			Done
79	07-Jul-22	Create Employee - Department Field should have dropdown	Open			Done, Pls Confirm
80	07-Jul-22	Edit Empliyee - Personal Email to be made non mandatory in database	Open			Done
81	07-Jul-22	Create Employe - Blood Group - Default value should be Not Provided	Open			Done
82	07-Jul-22	Create Employee - Official Email *: On entering the email id which is mandatory it is giving error of Official email field is required. This need to be fixed, due to error cant create employee	Open			Done
83	07-Jul-22	Leads Create: Contact No. - How do we enter ISD Number or Landline number in single field?	Open			Not Done
84	13-Jul-22	Under Leads Information - Add New Button should also be there next to Update Status Button	Open
	13-Jul-22	In Create Builder & Edit Builder - one more field with dropdown as Builder, CP Rent, CP Sale Purchase, Individual	Open

## Sheet2
Existing	Existing
Leads Create	Update Leads	Lead Information	Final Sequence of Leads Create, Update Leads, Leads Information
Date *	Lead Generation Date	Name	Lead Generation Date
Customer Name*	Name of Customer	Date	Contact Number *
Contact Number *	Email	Contact Number	Customer Name *
Customer Requirement *	Contact Number *	Location	Alt Contact Number 1
Buying Location *	Alt Contact Number 1	Email	Alt Contact Number 2
Source *	Alt Contact Number 2	Lead Status:	Customer Email
Lead Assigned To *	Customer Requirement	Customer Requirement:	Customer Type *
Lead Status *	Project	Lead Type	Customer Requirement *
Lead Type *	Location	Mode of Lead	Buying Location *
Number of Units	Mode of Lead	Assigned To	Source *
Customer Type	Assign Employees	Project	Lead Assigned To*
Customer Interaction	Lead Status	Number of Units	Lead Status *
Customer Profile	Lead Type *	Reference Name	Lead Type *
	Number of Units	Budget	Number of Units
	Reference Name	Rent Budget	Project
	Reference Contact Number	Emergency Contact Number:	Location of Customer
	Investment or End User	Reference Contact Number:	Featured Lead
	Budget	Location of Customer:	Show More Button	Budget for Property
	Location of Customer	Relationship	Customer Interaction	Rent Budget
	Customer Type	Booking Date	Customer Profile	Investment or End Use
	Relationship Contact Number	Investment or End User:		Regular Investor
	Relationship Contact Name	Customer Type		Reference Name
	Relationship	Emergency Contact Name:		Reference Contact Number
	Booking Date	Booking Amount:		Relationship Contact Number
	Booking Amount	Featured		Relationship Contact Name
	Booking Project	Regular Investor		Relationship
	Move to Common Pool	Customer Profile		Booking Date
				Booking Project
				Booking Amount