## Sheet1
S. No. | Details of Observation | Status | Remarks | Menu Name
1 | Once a new lead is added, some button should be there to go to it's edit action else once has to do repeated work to click on lead then find the desired customer and then click on edit. This is a lengthy process to add more details about the customer. | Done
2 | Space is not getting removed from mobile number, system should not allow space or special characters. | Done
3 | 1.5 Cr to 2 Cr missing from Budget | Done
4 | Relationship is by default getting selected and same is happening with Emergency Contact Name. | Pending
5 | Option to provide multiple name and number should be available for each customer. | Pending
6 | Booking date and Booking amount should be at last of Update leads | Done
7 | From the Update Lead page user should have option to go back to the histor of same customer or go back to leads page. | Done
8 | The first Customer Interaction is not getting captured any where while it was entered during Leads Creation and same is happening with Customer Profile. | Done
9 | How will Bulk Upload Status Appear in Dashboard | Pending
10 | What is Preference Type in Update Lead | Done
11 | In Dashboard - Leads - Time is not getting captured | Done
12 | Emergecy Contact Name ¦ Relationship ¦ Number | Done |  | Add ¦ update Employee
13 | Redirect button required on history update page. | Done
14 | Last Contacted Time ¦ Creation time and Follow up time | Done
15 | Next Follow up - Yellow and Red(When follow time over) | Done
16 | Mobile Number should be clickable and open in dialer | Done
17 | Lead Type - Lead Table | Done
18 | Lead -> Assigned Lead | Done
19 | Lead Add - Checkbox -> Featured | Done
20 | Show Green Star on name for Featured leads- Admin | Done
21 | Lead -Action ¦ Edit and History - Before Data | Done
22 | Lead History - Edit Lead button and Update History button | Done
23 | Remove Customer Profile from history and Add it in information section,Show all lead information like 9 and show more button to show all information. | Done
24 | Contact Number ¦ Alt Contact Number 1 and Alt Contact Number 2 | Done
25 | Location of Customer | Done
26 | Project Type - Customer Requirement | Done
27 | Project Dropdown with multiple Selection - Update History page | Done
28 | FLAT 1 BHK RTM – FLAT 4 BHK RTM | Done
29 | FLAT 1 BHK UC - FLAT 4 BHK UC | Done
30 | Reference - Reference Name ¦ Reference Contact Number | Done
31 | Customer Type - TENANT AND OWNER | Done
32 | Customer if Seleted TENANT OR OWNER - Then show Rent Budget Field | Done
33 | Regular Investor - YES ¦ NO – Lead Section | Done
34 | Emergency Contact Name - USING MOBILE NUMBER RELATIONSHIP Added | Pending
35 | Booked In Project - Dropdown | Done
36 | History Count and | Done
37 | Multiple Project Booking Option | Done
38 | User ID/Name should also appear in History Information for each entry. | Open
39 | Action Button should be available in Dashboard Leads section too | Open
40 | Status HIstory - Can be aligned towards left side so that more collumns can appear as of now too much space is wasted in extreme left | Open
41 | If a number is searched and no data is fount then there shuld be a button to Add New - as soon as add new is clicked after the number searched which is not in records, it should pick the search number in contact no to create a new lead so that same number need not be written again. This will save time of user | Open

## Sheet2
S. No. | Details of Observation | Status | Remarks